## Instruction
Instructions:
1. Complete screening during AWP stage 1;
2. Under description: Select the appropriate familiarity and complexity responses from the drop down box;
3. Complete project specific screening comments.
4. The level-rank result will be indicated in the matrix as low, medium or high
Notes:
1. This risk assessment is intended to address constructability only and excludes business or other risks;
2. All questions are weighed equally;
3. Unfamiliar = 3 or more Unfamiliar, Familiar = 1 or 2 are Type 2
formula:
If >2 questions are rated Unfamiliar then familiarity = Unfamiliar
If <3 questions are rated Unfamiliar then familiarity = Familiar
4. Low Complexity = 6 or more Low, High Complexity = 6 or more High
formulas:
If >5 questions rate "LOW" then complexity = LOW
If <6 questions rate "LOW" then complexity = HIGH

## Screening Tool
Construction Familiarity & Complexity Screening Tool
|  |  | Project Name |  |  | Level Rank Matrix
|  |  | Project General Description |  |  | Unfamiliar | Familiar | N/A
Scalable AWP |  |  | Review Date: |  | LOW | Medium | Low | 2
|  |  | Project Manager |  | HIGH | High | Medium | N/A
|  |  | Construction Manager |  |  |  |  | N/A
| No | Question | Process Advantage | Description Select best fit description from Drop Down Box s |  | Type | Screening General Comments Record key decisions and actions
Familiarity | 1 | Is Scope of Work (SOW) similar to previously executed projects? | Scope of Work familiarity | Duplicate project with scope of work similar to previously executed projects and has <50% scope change |  | Familiar
| 2 | Will the development be managed as a project or program | Project execution efficiency | Managed as a Program |  | Familiar
| 3 | Are the work packages reusable for this project? | Engineering and Construction Work Package production efficiency | Standardized design or >50% engineering and construction work packages are recycled from previous projects. |  | Familiar
| 4 | Regulatory and permitting requirement. | Corporate Social Responsibility, Regulatory, Reputation | Execution team has successfully completed project specific regulatory permitting requirements. |  | Familiar
| 5 | What type of construction contract is planned? | Project execution efficiency | Owner or EPC has partnered with select general contractors and assigns construction on a highest value bases |  | Familiar
| 6 | How is equipment and materials purchased? | Project procurement efficiency | Owner or EPC purchase equipment and material from an approved vendors list |  | Familiar
Complexity
Constructability Complexity | 1 | Is proposed facility is brownfield or greenfield? | Operations Interface, Ground Disturbance Ridk | Greenfield - No previous facilities existed above or below ground, new development will have minimum impact on operating facilities. New development is separated from the exiting facility by a minimum of 30 m (100 Ft.) |  | LOW
| 2 | What is number of separate construction areas? | Coordination, Interface, Battery limits | 1 or 2 adjacent areas; Shared resources can be utilized |  | LOW
| 3 | What is the count of construction disciplines involved in the project? | Coordination, work face density, Interface, Startup | < 7 of any of discipline: earthwork, foundations, structural, Buildings, mechanical equipment, piping, insulation, painting/coating/lining, electrical, Instrumentation and controls. |  | LOW
| 4 | What is the scope or count of mechanical, electrical, instrumentation and controls tie-ins? | Hot Work, Plant Outage Risks | Electrical, Instrumentation and Controls Only (EI & C), Hot Work with no Loss of production |  | LOW
| 5 | Are critical or engineered crane lifts required? | Coordination, scheduling, risk to operations | All crane lifts are standard |  | LOW
| 6 | What are the known geotechnical conditions? | Ground Disturbance Risk, water disposal, access, spoil piling | Ground Water Dewatering is not required and/or no rock excavation |  | LOW
| 7 | What type of excavation are required? | Ground Disturbance, Confined Space | 2 m (6.5 Ft) or less depth excavation with trench box and/or OSHA Type 1 or 2 Soils and/or , < 10% Hydro-Vac |  | LOW
| 8 | Will the project be constructed working at heights? | Working at Heights, Productivity | < 25% scope requires working above 2 m (6.5 ft.) height |  | LOW
| 9 | What seasons will the project will be constructed? | Productivity, Transportation, ideal schedule | Construction - Normal productivity, no seasonal impact |  | LOW
| 10 | Is the project planned on a compressed schedule? | Coordination, work face density, productivity | Construction is planned on day shift only and/or All EWP/CWP will be issued IFC prior to commencing construction. EPC phases are sequential |  | LOW
| 11 | Is project site remote? | Transportation, work force recruiting and turnover | Workers drive daily between project and place of residence, no subsistence |  | LOW
Complexity

## Lists
Familiarity Type
|  | 1 | 2 | 3 | 4 | 5 | 6
|  | SOW Familiarity | Portfolio, Program or Project | Project Information & Documentation | Permitting | Construction Contract Strategy | Equipment/Procurement Strategy
Familiarity | Unfamiliar | One-off project or a duplicate of a previously executed project and the scope of work had changed by >50%. | Managed as a Project | Customized engineering or <50% engineering and construction work package recycled from previous projects | Although capable, the execution team is not experienced in project specific regulatory permitting requirements. | Owner or EPC SCM formally request project specific proposals, evaluates and awards. | Owner or EPC SCM formally request project specific proposals, evaluates and awards.
| Familiar | Duplicate project with scope of work similar to previously executed projects and has <50% scope change | Managed as a Program | Standardized design or >50% engineering and construction work packages are recycled from previous projects. | Execution team has successfully completed project specific regulatory permitting requirements. | Owner or EPC has partnered with select general contractors and assigns construction on a highest value bases | Owner or EPC purchase equipment and material from an approved vendors list
Complexity - Constructability
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Complexity | Lo | Greenfield, Brownfield | Construction Area | Multi - Disciplines | Tie-Ins | Critical Crane lifts | Geotechnical Conditions | Excavation | Working at heights | Construction Season | Schedule Compression | Project Site Remote
| High | Greenfield - No previous facilities existed above or below ground, new development will have minimum impact on operating facilities. New development is separated from the exiting facility by a minimum of 30 m (100 Ft.) | 1 or 2 adjacent areas; Shared resources can be utilized | < 7 of any of discipline: earthwork, foundations, structural, Buildings, mechanical equipment, piping, insulation, painting/coating/lining, electrical, Instrumentation and controls. | Electrical, Instrumentation and Controls Only (EI & C), Hot Work with no Loss of production | All crane lifts are standard | Ground Water Dewatering is not required and/or no rock excavation | 2 m (6.5 Ft) or less depth excavation with trench box and/or OSHA Type 1 or 2 Soils and/or , < 10% Hydro-Vac | < 25% scope requires working above 2 m (6.5 ft.) height | Construction - Normal productivity, no seasonal impact | Construction is planned on day shift only and/or All EWP/CWP will be issued IFC prior to commencing construction. EPC phases are sequential | Workers drive daily between project and place of residence, no subsistence
|  | Brownfield - New development will be constructed where previous above or below grown facilities or within 30 m (100 Ft.) of existing above or below ground facilities exist. New development interface with existing operation | 3 or more adjacent or non-adjacent areas. Shared resources need to be coordinated and planned | > 6 of any of discipline: earthwork, foundations, structural, Buildings, mechanical equipment, piping, insulation, painting/coating/lining, electrical, Instrumentation and controls. | Mechanical only or Mech. and EI & C or Plant/System Shut Down and Loss of production | Critical crane lifts required | Ground Water Dewatering is Required and/or rock excavation | > 2 m (6.5 ft.) depth of excavation and/or OSHA Type 3 soil and/or requires shoring and/or >10% Hydro-Vac | > 25% scope requires working above 2 m (6.5 ft.) height | Reduced worker productivity due to sub-optimal seasonal weather i.e., High humidex or Low wind-chill | Construction planned on day and night shifts and/or all EWP/CWP will not issued IFC prior to commencing construction. EPC phases may overlap. | Workers commute between project and place of residence between shifts, Projects accommodations or subsistence and turnaround costs required. Seasonal Roads and bridges may impact transportation plan.

## Formula
LOW or HIGH RISK | Unfamiliar OR Familiar
LOW RISK | Familiar