# 



**IWP Preparation Timeline 120 Days**

Document Number: COP-WFP-SPD-06-2013-v1

Revision: A Release Date: 2013

# Pre IFC

120 days EWPs IFC

90 days CWPs IFC

60 days begin FIWP development

30 days FIWP

ready for release

10 days print FIWP hard copy



Develop path of

construction Pre IFC develop Engineering

document/CWP/ FIWP release plans

Workface Planner manpower requirements based on release plan

Develop FIWP templates

EWP checklist

Release IFC EWPs as per agreed upon schedule

30 days to develop CWPs

CWP Checklist

Order shorts

Purchase field material Order tools and equipment

Confirm material suppliers will meet Required at Site dates Subcontractor contractor requirements

Begin populating FIWPs

Confirm material, tool and equipment delivery dates

Check resources FIWP readiness checklist

Develop Back Log or “Plan B” FIWPs

Integrate plans with

other disciplines

Add to 3-4 week look ahead

Confirm material and equipment received Get sign off

Print Hard Copy

of FIWPs that are 100% ready

Note: Initial procurement is outside the scope of this timeline

Author: D Coughlin

Approver: COAA WFP Committee

Page 1 of 1 IWP Timeline.vsd