








# Document Number: COP-WFP-WFD-02-2013-v1



































Installation Work Package Life Cycle Overview



Regular Superintendent meeting to

Create Electronic IWPs

## 1 Creation



Create IWP release schedule

Monitor

Constraints

Notify required

***2***

Send sequence and content of IWP to Document Control

identify task groupings

## Electronic Package

support trades

## Document Control Interface

Close out

## 5 IWP Close Out

Hard copy IWP created

Report Progress

Report IWPs that are complete

## Control of the IWP in the field

***4***

Issue IWP to field once constraints are satisfied

Remove items not completed

Leave in field until completion

Yes Complete No

Monitor

completion

status in the field

Field executes the work

## 3 Issuance to the Field

*Author: Robin Mikaelsson Approver: COAA WFP Committee*

*Page 1 of 1 IWP Lifecycle 0*