

# Document Number: COP-WFP-WFD-06-2013-v1



Installation Work Package Life Cycle

#4 Control of IWP in the Field

Return IWP to Planning department



Planning department files complete IWPs

Confirm progress report

See #5 IWP Close Out (A)

Completed Items

See #3 IWP Issuance to the field (A)

Monitor the status until complete

Remove unfinished tasks for repackaging

Removed Items

See #1 Electronic IWP creation (A)

YES

YES

Repack

Planning department records progress from field

Is the IWP 100% complete NO within the scheduled time

frame?

Is it Feasible for IWP to NO remain in the field?

Is the IWP to be held or unfinished items to be

repackaged

Hold

Return IWP to Planning department

Monitor IWP until Hold is removed

See #3 IWP

Issuance to Field (A)

# Author: Robin Mikaelsson Approver: COAA WFP Committee

*Page 1 of 1 WFP-WFD-2013-146-A IWP Lifecycle 4.vsd*