# Path of Construction Process

## Scoping	DBM	EDS

Operational Process Assets

WorkFace Planning Implemented

Constructability Implemented

Project Management

Enterprise Factors

Industrial Relations objectives

Project Risk Register

Project Charter

Project Management Strategy

Scope Statement

Project Execution Plan (PEP)

Operations C&SU

Start Up Sequence Priorities

EDS C&SU Plan

Construction Risks

Site/Facilities Plan

Path of Construction

Modularization. Pre-assembly Strategy

Construction Management

Construction Expertise

Construction	 Risk Register

DBM Construction Execution PLan

Construction Execution Plan

Review Constructability Log

Participative Planning

Heavy Lift Plan

CWP / EWP

Plan

Contracting Plan

FIWP Release Plan

Continued on Page 2 - EDS

Engineering

PFDs

Preliminary Plot Plan

EWP

Development

DBM

Plot Plan

To PEP

Project Controls

To PEP

Level I Schedule

WBS

Level II Schedule

Level III Schedule

Supply Chain

Long Lead Items

DBM

Procurement Strategy

To PEP

# Path of Construction Process

## DBM	Execution

Project Management

Project Execution Plan

Progressive Elaboration

Project Execution Plan

Execute

Operations C&SU

EDS C&SU Plan

C&SU Plan

Execute

WorkFace Planning Implemented

Constructability Implemented

Construction Risk Identification

DBM Construction Execution PLan

Progressive Elaboration

Review Path of Construction

Modularization. Pre-assembly Strategy

EDS Construction Execution PLan

Execute

Construction Management

YES

Change

NO

EDS

Required?

Heavy Lift Plan

YES

Review / Modify Construction Plans

CWP / EWP

Plan

FIWP Release Plan

Progressive Elaboration

Contracting Plan

Engineering

EWP

Development

EDS Engineering Plan

Execute

Project Controls

Level 4 Schedule	Level 5 Schedule

Execute

Supply Chain

DBM

Procurement Strategy

Progressive Elaboration

Procurement Plan

Execute